## Summary & Highlights
Production Implementation Runbook
Release Summary
Release # | CHG0240767
Release Changes
DWH Impact | N/A
QA Sign off date | 2018-09-28
UAT Sign off date | 2018-09-28
Change Highlights
Once data was input, and button [Generate and Send] clicked, application shows error "The record with the CPF or Passport number has been processed correctly, but failed to send the email". This is a Regulatory issue due Brazilian Laws enforce users to carry this certificated during traveling, the issue is that users can receive by email certificate and there is no workaround, this release provides more information about error and a workaround (certificated can be downloaded]
URL to be used during maintanence window
N/A
Support Tickets
Ticket # | Support Group
NA
Corporate ADM

## Detailed Steps
Production Implementation Runbook
S.No | Task | Assigned to | Duration | Start Time (DD/MM/YYYY CST) | End Time (DD/MM/YYYY CST) | Status
1 | Release Web Site | Mendoza, Leyver | 30 Min | 2018-09-28 17:00 | 2018-09-02 17:30 | Complete
2 | Release DB Objects | Mendoza, Leyver | 30 Min | 2018-09-28 17:00 | 2018-09-02 17:30 | Complete
5
6
7
8
9
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Corporate ADM

## Contacts
Production Implementation Runbook
Org | Contact List | Home | Office | Cell | Email
AIG | Leyver, mendoza |  | +52 55 5488 4667 |  | Leyver.mendoza@aig.com
AIG | Chavez, Alfredo |  | +52 55 5488 4510 |  | Alfredo.Chavez@aig.com
AIG | Patlán, Alejandro |  | +52 55 5488 4735 |  | Alejandro.Patlan@aig.com
Corporate ADM

## Rollback Steps
Production Implementation Runbook
Steps to Rollback
1 | Restore Web Site
2 | Restore DB
Corporate ADM