## Implementation Instructions
Implementation Instructions
APP | MASTERCARD-AP
Path (app) | D:\NAC-Sites\mastercard\ap\ap-mwi
Path (admin) | D:\NAC-Sites\mastercard\ap\ap-mwi-admin
Version | v1.4.5
Rollback Version | v1.4.4
Sequence | Team | Task Name | Source | Destination
DBA
1 | DBA | Run scripts (ordered by name): | #N/A | db [master]
Middleware
1 | Middleware | Backup folder | D:\NAC-Sites\mastercard\ap\ap-mwi | MASTERCARD-AP-App-backup-AAAAMMDD.zip
2 | Middleware | Backup folder | D:\NAC-Sites\mastercard\ap\ap-mwi-admin | MASTERCARD-AP-Admin-backup-AAAAMMDD.zip
3 | Middleware | Delete Files | #N/A
4 | Middleware | Copy and Paste (With Replace) | #N/A | D:\NAC-Sites\mastercard\ap\ap-mwi
5 | Middleware | Copy and Paste (With Replace) | #N/A | D:\NAC-Sites\mastercard\ap\ap-mwi-admin
6 | Middleware | Edit Config File | D:\NAC-Sites\mastercard\ap\ap-mwiappSettings.config
7 | Middleware | Edit Config File | D:\NAC-Sites\mastercard\ap\ap-mwi-adminappSettings.config
8 | Middleware | Restart Services | iisreset /restart | cmd (admin)

## Rollback
Rollback Version
APP | MASTERCARD-LACR
Rollback Version | v1.4.4
Sequence | Team | Task Name | Source | Destination
DBA
1 | DBA | Run scripts (ordered by name): | #N/A | db [master]
Middleware
1 | Middleware | Delete Folder | D:\NAC-Sites\mastercard\ap\ap-mwi
2 | Middleware | Delete Folder | D:\NAC-Sites\mastercard\ap\ap-mwi-admin
3 | Middleware | Restore Folder | MASTERCARD-LACR-App-backup-AAAAMMDD.zip | D:\NAC-Sites\mastercard\ap\ap-mwi
4 | Middleware | Copy and Paste (With Replace) | MASTERCARD-LACR-Admin-backup-AAAAMMDD.zip | D:\NAC-Sites\mastercard\ap\ap-mwi-admin
5 | Middleware | Restart Services | iisreset /restart | cmd (admin)